Location Map of the East African Community

Table of Contents

1	INTRODUCTION	3

1.1	The Assignment	3

1.2	Background to the East African Community	3

1.3	The East African Community	3

1.4	EAC Transport Corridors	4

1.5	The United Nations Environment Programme	6

1.6	Contract Particulars and Effective Date	6

1.7	Purpose and Structure of this Report	7

1.8	Rationale for the Assignment	9

1.9	What the Assignment builds on	9

2	OBJECTIVES OF THE STUDY	10

2.1	Overall Objectives	10

2.2	Specific Objectives	10

3	SCOPE AND METHODOLOGY OF THE     ASSIGNMENT	11

3.1	Scope	11

3.2	Specific study elements	11

3.3	Methodology	12

4	PRELIMINARY REVIEWS AND FINDINGS	18

4.1	Situational Diagnosis and Baseline Assessments	18

4.2	Current status of e-mobility in the EAC Region	19

5	STAKEHOLDER ANALYSIS AND MAPPING	22

5.1	Identification of Stakeholders	22

5.2	Global, Continental and Regional Agencies	22

5.3	EAC Partner States	24

6	DRAFT EAC REGIONAL E-MOBILITY STRATEGY AND POLICY	36

7	CONSULTANT’S MOBILIZATION STATUS	36

8	WORK PLAN	37

9	NEXT STEPS	38

# INTRODUCTION

## The Assignment

On 15th September 2026, the United Nations Environment Programme (UNEP) signed a contract with Eng. Hosea Nyangweso, a Transport Consultant, to conduct a study on the development of a regional e-mobility policy and strategy in the East African Community region, which will guide the coordinated energy transition in the regional roads sector. This report sets out the foundation of the assignment. It introduces the East African Community and the transport corridors that connect it, the role of the United Nations Environment Programme in commissioning this work, the particulars of the contract under which it is delivered, and the rationale and existing frameworks on which the study is built.

## Background to the East African Community

The East African Community stands at a real opportunity to advance regional electric mobility. The market is there, but a common framework that lets all Partner States function as one is missing, and that is the subject matter of this report.

This report is the starting point for the development of a Regional Electric Mobility Policy and Strategy for the Community, commissioned by the United Nations Environment Programme on behalf of the EAC and delivered in close coordination with the EAC Secretariat throughout. It outlines: the structure of the assessment; how the work will be undertaken; how governments, businesses and the community throughout the region will be engaged; what will be included in each output; and when it will be put in place. It is the first of six deliverables and becomes the reference point against which the rest of the assignment is measured.

## The East African Community

The East African Community (EAC) is a regional intergovernmental organization of eight Partner States, namely: The Republic of Burundi, the Democratic Republic of the Congo, the Republic of Kenya, the Republic of Rwanda, the Federal Republic of Somalia, the Republic of South Sudan, the United Republic of Tanzania and the Republic of Uganda. The EAC has its headquarters in Arusha, Tanzania.

The figure below shows the member countries of the EAC.

Figure 1-1: East Africa Community Map

## EAC Transport Corridors

There are eleven major corridors in the EAC according to the EAC Infrastructure Road Transport sub-sector, namely: Northern Corridor, Central Corridor, Dar-es-Salaam (TAZARA) Corridor, Namanga Corridor, Sumbawanga Corridor, Sirari Corridor, Coastal Corridor, Mtwara Corridor, Tanga Corridor, Gulu Corridor and LAPSSET Corridor, as shown in the map below.

Figure 1-2: East Africa Community Transport Corridors’ Map

The Treaty for the Establishment of the East African Community includes cooperation on infrastructure, energy, environment, trade and industrial development, all of which are relevant to the transition to sustainable mobility. The EAC Vision 2050 sets out a long-term ambition to transform the region into an upper-middle-income area through, among other pillars, infrastructure development, industrialization and environment and natural resource management. The Vision places emphasis on affordable and efficient regional transport, energy systems and stronger regional competitiveness, making e-mobility a highly relevant cross-sectoral agenda for the Community. Similarly, the EAC climate framework recognizes the need for a coordinated regional response to climate change, including action in energy security, infrastructure and environmental sustainability. The EAC Climate Change Master Plan identifies infrastructure and energy among the key climate-sensitive sectors requiring regional planning and implementation support.

## The United Nations Environment Programme

The United Nations Environment Programme (UNEP) is the United Nations systems designated entity for addressing environmental issues at the global and regional level. Its mandate is to coordinate the development of environmental policy consensus by keeping the global environment under review and bringing emerging issues to the attention of governments and the international community for action.

The overall objective of the Industry and Economy Division of UNEP is to encourage decision makers in government, local authorities and industry to develop and adopt policies, strategies, practices and technologies that promote sustainable patterns of consumption and production, make efficient use of natural resources, ensure safe management of chemicals and contribute to making trade and environment policies mutually supportive. It promotes the development, use and transfer of policies, technologies, economic instruments, managerial practices and other tools that assist in environmentally sound decision-making and the building of corresponding activities.

UNEP has been actively supporting electric mobility initiatives globally and across Africa, including in several East African Community Partner States, and has contributed to harmonising fuel and emission standards in Africa to create stronger demand signals and a more coherent electric mobility market.

This assignment will be managed by the Sustainable Mobility Unit of UNEP.

## Contract Particulars and Effective Date

Table 1-1: Contract particulars

| Item | Particulars |
| --- | --- |
| Assignment | Consultancy Services for the Development on an EAC E-Mobility Policy and Strategy |
| Client | The United Nations Environment Programme, Sustainable Mobility Unit |
| Recipient | The East African Community |
| Programme Reference | JO 283547:UNEP ODED IED IIB MU |
| Contract Reference | PO 2500411512 |
| Consultant | Eng. Hosea Nyangweso |
| Effective Date | 15th September 2026 |
| Duration | Six (06) Months |
| Contract end date | 15th March 2027 |
| Reporting lines | UNEP (Sustainable Mobility Unit) and EAC (Directorate of Infrastructure, Transport and Works Department) |
| Deliverables | Delivery No.; Description. 1; Inception Report (This report). 2; Draft Diagnostic and Assessment Report.. 3; Final Diagnostic and Assessment Report. 4; Draft EAC Regional E-Mobility Strategy and Policy. 5; Draft Implementation Roadmap and Action Plan. 6; Draft Monitoring, Evaluation and Learning Framework. 7; Final EAC Regional E-Mobility Strategy and Policy. 8; Final Implementation Roadmap and Action Plan. 9; Final Monitoring, Evaluation and Learning Framework. |

## Purpose and Structure of this Report

This Inception Report is the first deliverable of the assignment. It records the preliminary work undertaken during the inception period, including baseline data and stakeholder mapping, confirms the scope of the assignment as described in the Terms of Reference, refines the work plan and establishes the basis on which the remainder of the assignment proceeds.

The report serves three purposes. It informs the Client of the position reached at the close of the inception period, including any consultations held, the data collection methodology and instruments to be used and the preliminary analysis completed. It sets out for confirmation those matters which shape the work to follow and records the matters requiring Client decision, in particular the need for field visits/consultations. Further, it will in effect be the basis for tracking compliance with the TORs.

The report is structured as shown in the table below.

Table 1-2: Structure of the Inception Report

| Chapter | Content |
| --- | --- |
| 1 | Introduction: the East African Community and its transport corridors, the role of the United Nations Environment Programme, contract particulars, the purpose and structure of this report, and the rationale and existing frameworks the assignment builds on |
| 2 | Objectives of the study: the overall objective and the specific objectives guiding the assignment |
| 3 | Scope and specific elements and methodology of the assignment: the Partner States covered and the technical areas to be assessed and how they will be assessed |
| 4 | Preliminary reviews and findings: the approach to the diagnostic and baseline assessment, and the initial country-by-country status of e-mobility across the eight Partner States |
| 5 | Stakeholder analysis and mapping: institutions identified at global, continental, regional and Partner State level, and how they will be engaged |
| 6 | Approach to the draft EAC Regional E-Mobility Strategy and Policy |
| 7 | Consultant's mobilisation status: Presents the team that will assist the lead consultant to carry out the assignment and their roles. |
| 8 | Work plan: Proposes the time frames within which each of the deliverables will be prepared, including allowances for reviews by stakeholders and conveying of validation meetings. The work plan may be adjusted to suit specific requirements of the assignment or as shall be agreed between the parties. |
| 9 | Next steps: Presents the activities for the deliverable immediately following this report |

## Rationale for the Assignment

East African Community is increasingly recognized as one of the most dynamic e-mobility regions on the continent, with rising adoption of electric two- and three-wheelers, emerging Electric Vehicle assembly, charging infrastructure deployment and growing policy attention across several Partner States. However, progress remains uneven, with differences in fiscal incentives, battery and charging infrastructure standards, charging frameworks, industrial policy, data systems, level of awareness and technical capacity. A regional policy and strategy can help reduce fragmentation, support economies of scale, and accelerate market development in line with the EAC integration agenda.

Economically, the region is highly vulnerable to volatile global oil prices. Environmentally, the combustion of fossil fuels is a primary driver of greenhouse gas emissions and climate change, exacerbating extreme weather events that threaten the agricultural and water systems upon which the East African Community depends. A transition to electric mobility offers a compelling solution to these challenges, promising to reduce import dependency, stabilise transport costs, cut emissions, improve air quality and position the EAC as a leader in clean technology.

In response to these challenges and in order for the EAC countries to address them collectively, UNEP, on behalf of the EAC, has engaged an international consultant to develop an EAC Regional E-Mobility Policy and Strategy, together with an implementation roadmap, action plan and monitoring framework.

## What the Assignment builds on

The Study will build on work already done and initiatives that are underway in the countries to develop a coherent regional policy framework that will enable the region to move as one block in advancing e-mobility as a viable transition from fossil fuel modes of road transport. It will also take into account the guiding principles contained in the continental framework developed by the AU, UNEP and UNECA in 2025 and benchmark with the outcomes of global programmes carried out in sub-regions of similar socio-economic stature to EAC.

Three developments give this assignment firm ground to stand on now:

- The EAC's own development blueprint for the next five years, adopted by the Heads of State of the Community in March 2026, has provided for industrialization, infrastructure and green economy as some of its major priorities. An EAC regional e-mobility policy under this development cycle will be fully situated in that space.

- The EAC’s regulations on vehicle assembly and manufacturing, which were implemented in July 2026 (albeit not fully to be enforced until July 2027), for the first time created a common EAC measure of local assembly and manufacturing. Previously, a company in one country doing little more than bolting parts together to complete a kit would consider it the same as manufacturing in another country. These regulations are still new, so partner states have not established how this will fit in e-mobility s. That is a crucial piece of work for this assignment.

- The UN Economic Commission for Africa, in collaboration with UNEP and the African Union Commission, published the continental electric vehicle policy guidance in August 2025. It spells out what the continent expects to see in any regional policy: local manufacturing, charging infrastructure and energy readiness, access to finance, public awareness and skills, harmonized standards, vehicle performance rules, environmental sustainability and fair treatment of workers, and clear governance and monitoring arrangements. The EAC policy will have to be designed in direct response to each of these pillars, so that it reads like the region's practical implementation of the continental agenda.

Further, the Treaty for the Establishment of the East African Community already gives the Community the legal standing it needs for this work, through its provisions on the customs union and common market, on industrial development, on transport and energy cooperation, and on the environment, so the task ahead is to put that existing authority to use.

# OBJECTIVES OF THE STUDY

## Overall Objectives

The overall objective of this assignment is to develop an EAC Regional E-Mobility Strategy and Policy that provides a practical, coordinated and actionable framework for accelerating the adoption of electric mobility across EAC Partner States, while promoting regional policy harmonisation, private sector participation, renewable energy integration, industrial development, green jobs and reduced transport-related emissions. Further, to contribute to the vision of the East African Community as a leader in sustainable mobility on the continent, with widespread adoption and local production of electric vehicles, contributing to reduced carbon emissions, improved air quality, and stimulating job creation while furthering the region's energy transition.

## Specific Objectives

The specific objectives are:

- Conduct research on the evolution of e-mobility in other regions of Africa and the World with similar stature to the EAC; outline how it evolved, the challenges faced, the current situation and quantify benefits that accrued.

- Assess the current status of e-mobility across EAC Partner States, including EV ownership shares compared to ICE vehicles, awareness, market development, policy and regulatory frameworks, infrastructure readiness, financing conditions, industrial opportunities and institutional arrangements.

- Identify key barriers and opportunities for regional e-mobility adoption, including technical, legal, fiscal, institutional, social, environmental, and financial dimensions.

- Develop a draft regional policy and strategy framework for e-mobility, including a policy matrix containing recommendations for harmonized standards and specifications, incentives, data systems, battery end of life management and EV disposal and regulatory approaches.

- Propose an EAC regional implementation roadmap and action plan with short-, medium- and long-term priorities including financing needs. Identify opportunities for local assembly, parts manufacturing, skills development and value chain participation within the EAC.

- Recommend mechanisms for mobilising public and private finance, including catalytic investments, blended finance mechanisms and pilot projects.

- Recommend a set of regionally harmonised tariff and tariff-based incentives for adoption by the EAC Partner States for accelerating affordable e-mobility uptake.

- Facilitate regional consultations and validation processes to support endorsement by EAC technical and policy organs.

# SCOPE AND METHODOLOGY OF THE     ASSIGNMENT

## Scope

The assignment will cover all eight Partner States of the EAC. However, in the conduct of research and benchmarking studies, limited online assessments will be made on countries and regions outside the EAC

## Specific study elements

The following key elements that are key to the development of electric mobility will be assessed:

- Power generation, distribution and access to power in each Partner States to determine the readiness for the roll-out of e-mobility;

- Charging and battery swapping infrastructure, grid readiness for e-mobility integration, renewable energy integration opportunities, and implications for power systems, solar-powered charging, decentralized energy solutions, and cross-border interoperability;

- Financing barriers and opportunities, including tax treatment, concessional finance, business models, leasing, battery financing, public procurement and investment de-risking;

- Opportunities for local assembly, spare parts manufacturing, local content, skills development and entrepreneurship in the e-mobility value chain including battery end of life management.

- Social inclusion considerations, including implications for women, youth, informal transport operators and other groups with special needs (persons with disability)

- Environmental considerations, including battery lifecycle management, recycling, second-life use, waste management, and broader circular economy issues.

- Assess opportunities for local manufacturing, battery value chain participation, and regional supply chain integration.

## Methodology

3.3.1 	Overall Approach

The work has various tracks.

- It will involve research which will develop an evidence base that analyses published information, laws, tax rates, energy data and industry claims;

- Country data collection will acquire evidence from each Partner State by direct commission;

- Stakeholder consultations will collect the views of government, business, finance and civil society.

- A comparative review will assess how other countries with relevant starting points have managed energy transition.

The four tracks will lead to a single drafting process that will yield four publications in series.

3.3.2 Data Collection

Country-level data will be collected primarily through virtual means in the first instance: stakeholder websites, published research, regulator and utility reporting, and the structured data request issued through the EAC Secretariat. Where virtual data collection is insufficient and it is not possible to establish a credible baseline for a given Partner State or thematic area, limited physical missions will be arranged, following consultation with and approval by UNEP and the EAC.

3.3.3 Data Validation

All data will be shared with the relevant national focal point for validation and included by them in the relevant draft or final report. This validation stage extends to the data that is published as part of the actual report, for example, vehicle registrations or tariff levels, as well as to the factual claims and analysis derived from interviews or the legal reviews. Where a figure cannot be corroborated by a national source, it will be retained only where at least one other independent source supports it, and will be presented as an estimate and not as a verified figure. Where sources disagree materially, the range will be shown rather than a single number selected without explanation.

3.3.4 Monitoring, Evaluation (M&E), and Analytical Framework

To transition this study from a static baseline assessment into a dynamic, long-term tracking system, the data architecture is governed by a formal Monitoring and Evaluation (M&E) Framework. The information is structurally categorized across six distinct dimensions to enable cross-country comparison, while being supported by standardized Reporting Protocols to guide future database updates.

A. Thematic Performance Categories

Data points within the master relational database are grouped and mapped against the following primary dimensions:

- Power Generation, Supply Quality, & Access: Tracking grid capacity expansion factors, renewable energy shares, and grid stability indices (SAIDI/SAIFI).

- Recharging Infrastructure & Grid Readiness: Monitoring spatial charging station counts, protocol interoperability, and utility distribution-level peak load impacts.

- Macro-Finance & Capital Stacking: Logging catalytic grants, commercial debt/equity infusions, and consumer retail asset-financing structures (e.g., PAYG models).

- Industrial Value Chains & Local Assembly: Benchmarking regional manufacturing capabilities, local component integration, and domestic employment volumes.

- Just Transition & Social Inclusion: Evaluating localized skill-gaps, mechanic upskilling programs, and labor mitigation strategies for ICE job displacement.

- Circular Economy & Lifecycle Management: Tracking battery degradation metrics, second-life stationary storage applications, and end-of-life disposal protocols.

B. Institutional Reporting Protocols & Update Mechanisms

To ensure systematic database longevity, the indicators are tied to an institutionalized data-maintenance workflow. The table below details the target frequency, primary regional custodians, and extraction methods required to refresh the data:

| M&E Dimension |  | Core Indicators to Track |  | Primary Data Custodian | Update Frequency |  | Reporting Protocol & Update Mechanism |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Grid & Power Readiness |  | Capacity splits, outage frequencies, clean energy generation ratios. |  | National Utilities (e.g., Kenya Power, TANESCO, REG) & AfDB ERI database. | Annual |  | Automated pulling from annually published utility indicators and the African Development Bank Portal. |  |
| Tariffs & Regulations |  | Customs HS codes, duty/VAT adjustments, standard approvals. |  | EAC Secretariat Customs Directorate & National Bureaus of Standards. | Bi-Annual |  | Direct review of gazetted Finance Acts and East African Standards (EAS) catalog updates. |  |
| Fleet & Infrastructure |  | EV vs. ICE registration volumes, spatial charger network growth. |  | National Revenue Authorities, Transport Ministries, & Charger Providers. | Quarterly |  | Scripted spatial mining against Google Maps API paired with data requests to national vehicle registries. |  |
| Market & Finance Telemetry |  | Operational unit economics, commercial funding volumes. |  | Private E-mobility Operators, regional climate funds, and local pilot telemetry. | Continuous |  | Integration of anonymized telemetry sharing agreements and API endpoints with leading regional logistics/fleet companies. |  |
| Socio-Economic Impacts |  | Skilled labor availability, displacement metrics, second-life usage. |  | National Manufacturing/Mechanic Associations & Environmental Bodies (NEMA). | Biennial |  | Targeted stakeholder consultation surveys and regional labor census updates. |  |

C. Baseline Tracking and Policy Feedback Loops

By anchoring the analytical framework within these strict reporting protocols, this M&E structure supports the dynamic tracking functionalities detailed in Chapter 4. It establishes a measurable, time-series repository. When a Partner State adjusts a tariff or adopts a new battery standard (Dataset 32), the change automatically updates the corresponding indicator. This provides immediate, data-driven feedback on regional integration, transport decarbonization trajectory, and long-term infrastructure investment viability across the East African Community.

3.3.5 Comparative Review

In parallel with the regional assessment, a review of good practice across the continent and globally will be undertaken, with a focus on those regions and countries of a similar socio-economic status to the EAC. This has a dual purpose: both in identifying which good practices could be taken and adapted to the EAC context and also serving as a benchmark against which the Partner States are able to situate their own on a regional and global level.

3.3.6 Description of the Datasets

The table below is a brief description of datasets to be used in the diagnostic analysis for the e-mobility project. It gives an oversight of the description of each dataset and outlines the role each dataset will play in this project.

Table 3-1: Description of the Datasets

| No. | Dataset Title | Description | Role in the Project | Data Source & Acquisition Strategy |
| --- | --- | --- | --- | --- |
| 1. | Countries | Dimension table listing 8 EAC Partner States with ISO codes, accession years, population, GDP, and currency fields. | Acts as the foundational anchor table/spine holding the entire relational database together for cross-country queries. | Baseline: World Bank Development Indicators & EAC Secretariat official updates. |
| 2. | Market fleet | Verified electric vehicle registration data broken down by country, year, vehicle segment, propulsion type, and data confidence. | Provides the quantitative baseline against which all progress targets, recommendations, and adoption targets are calibrated. | Baseline: National Transport Ministries & Revenue Authorities (e.g., KRA, TRA). Future: API tie-ins with digital vehicle registries. |
| 3. | Policy inventory | Comprehensive collection of e-mobility policy instruments across all eight EAC states including fiscal incentives and regulatory statuses. | Serves as the technical foundation for the policy matrix deliverable and supports comparative analysis of regional regulatory approaches. | Baseline: Published National E-mobility Policies, Climate Strategies, and gazetted ministerial directives across the EAC. |
| 4. | Fiscal tariffs | Comparative duty and VAT rates applied to internal combustion engine (ICE) vehicles versus electric vehicles across EAC states | Underpins the tariff harmonization recommendation and directly feeds into cost-benefit modeling for expanding the regional EV market. | Baseline: EAC Common External Tariff (CET) Handbook and national finance acts. |
| 5. | Power system | Grid capacity, fuel mix splits, access rates, peak demand, reserve margins, and grid carbon intensity for each EAC state. | Provides the power-sector readiness assessment, renewable energy integration analysis, and emissions-reduction quantifications. | Baseline: National Utility annual reports (e.g., Kenya Power, TANESCO, REG, UMEME) and Power Africa sheets. |
| 6. | Financing | Catalogue of sovereign and philanthropic grants, commercial finance (debt and equity), concessional finance, blended finance, guarantees, and pay-as-you-go (PAYG) mechanisms supporting e-mobility. | Provides the financing landscape assessment and directly supports investment de-risking recommendations for future projects. | Baseline: Climate fund registries (GCF, GEF), development bank portfolios (AfDB), and regional e-mobility industry updates. |
| 7. | Industrial value chain | Tracked snapshot of companies active in e-mobility value chain stages (assembly, battery, recycling) with capacity and employment figures. | Provides the industrial capacity baseline and supports the development of regional supply chain and value chain strategies. | Baseline: National Investment Authorities, manufacturing associations, and direct e-mobility startup disclosures. |
| 8. | Battery End of Life (eol) | Battery end-of-life data organized by chemistry, volume, collection rates, facility counts, regulatory status, and second-life application metrics (repurposing capacity, stationary storage suitability, and cost-benefit models). | Provides the circular economy assessment and supports the formulation of environmental safeguard recommendations. | Baseline: Regional environmental management acts (NEMA) and academic technical degradation parameters. |
| 9. | Country qualitative | Qualitative and proxy-based profiles for five data-scarce EAC states capturing market sizing proxies, stakeholder consultation synthesis, infrastructure readiness indicators, primary vehicle segments, and key institutional barriers. | Provides qualitative context for data-scarce countries and acts as the explicit justification for data system recommendations. | Baseline: Proxy metrics extrapolated from neighboring markets, draft national frameworks, and local expert consultation matrices. |
| 10. | EV charging infrastructure | Mapping of EV charging stations across East Africa tracking locations, providers, charger protocols, pricing, and up-time metrics. | Supplies foundational data for regional spatial modeling, network gap assessments, and border-corridor route planning strategies | Derived: Algorithmic extraction script executing spatial mining against Google Maps API data. |
| 11. | Fuel: Motorcycle daily operations | Historical daily operational logs tracking boda-boda driver telematics alongside operational, financial, and fuel consumption parameters. | Supplies foundational operational data required to build macroeconomic financial models, driver income simulations, and fleet transitions. | Derived: Secured from published digital vehicle tracking and transport telematics empirical research studies online. Link: https://data.mendeley.com/datasets/nv3rkn24zv/1 |
| 12. | Fuel: Motorcycle trip operations | GPS-tracked trip-level segment data for electric motorcycle riders in Nairobi capturing timestamps, distance, and speed metrics | Provides the behavioral evidence base for the 2W/3W segment to support operational cost modeling and charging network design. | Derived: Secured from published digital vehicle tracking and transport telematics empirical research studies online. Link: https://data.mendeley.com/datasets/nv3rkn24zv/1 |
| 13. | Electric motorcycle daily operations | Daily aggregated operational and financial metrics combining rider distance, road durations, revenue, maintenance, and charging energy costs. | Serves as the commercial viability assessment for evaluating unit economics, business model comparisons, and operator affordability. | Derived: Secured from published digital vehicle tracking and transport telematics empirical research studies online. Link: https://data.mendeley.com/datasets/nv3rkn24zv/1 |
| 14. | Electric motorcycle trip data | High-resolution micro-level trip segment dataset detailing exact route paths, spatial coordinates, timestamps, and speed profiles | Serves as the primary spatial and operational analytics engine for infrastructure location selection and utility grid load profiling. | Derived: Secured from published digital vehicle tracking and transport telematics empirical research studies online. Link: https://data.mendeley.com/datasets/nv3rkn24zv/1 |
| 15. | Main Sheet (Africa EV Readiness) | Master repository aggregating the 16 readiness, impact, and macroeconomic indicator scores (derived from the sub-sheets) across all 54 African nations. | Acts as the primary underlying database feeding all summary rankings, benchmarking figures, and strategic report frameworks. | Acquired: Pre-compiled multi-sheet workbook sourced from the Energy for Growth Hub. Link: https://energyforgrowth.org/article/2025-update-africa-ev-readiness-and-impact-index/ |
| 16. | EV Incentives | Inventory of legislative and regulatory incentives adopted by national and sub-national African governments through 2023. | Supplies qualitative evidence for the Enabling Policies indicator component within the master Readiness score | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 17. | Quantitative EV Adoption Scenario Modeling (EAC Targets vs. Accelerated Pathways) | Quantitative modeling of additional electricity generation and grid capacity expansion factor requirements across multiple adoption scenarios (including existing partner states' targets, conservative baselines, and accelerated adoption pathways). | Direct input into the Grid Infrastructure component evaluations of the baseline Readiness Score. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 18. | Grid Reliability | Data capturing electrical grid stability, outage frequencies, and annual interruption durations across African nations | Serves as a core sub-indicator for power infrastructure quality evaluations within the technical Readiness scoring. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 19. | Current Rate of Motorization | Country-level vehicle ownership density figures per capita across Africa benchmarked as of 2016. | Feeds directly into the Market scale category metrics of the finalized Readiness index | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 20. | Electricity Regulatory Index | Evaluation of power sector regulatory maturity and governance framework indicators based on African Development Bank metrics | Serves as a primary Power Sector Maturity sub-indicator utilized within the technical Readiness scoring index | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 21. | Relative Affordability | Economic comparison evaluating the operational fuel cost per 100 kilometers of driving an EV versus a traditional ICE vehicle. | Core metric used to evaluate the EV Affordability component within the foundational Readiness index. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 22. | Access to Finance | Financial inclusion metric tracking the percentage of adult populations with access to formal credit or mobile money services. | Represents consumer financing feasibility parameters used within the macro-Readiness dimension. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 23. | Electricity Generated from Clean Energy | Breakdown of national power generation profiles highlighting renewable vs. fossil fuel generation percentage shares. | Key sub-indicator used to determine Climate impact scores within the environmental Impact scoring framework. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 24. | CO2 from Transportation | Sectoral emissions assessment tracking the proportion of total fuel combustion CO2 emissions produced by transport activities. | Forms the core climate metric for calculating transport decarbonization priorities within the overall Impact score. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 25. | Fossil Fuel Import Dependence | Macroeconomic trade exposure assessment measuring transport fuel import volumes relative to total net national consumption. | Represents macroeconomic trade balance impacts and foreign exchange relief factors within the Financial Impact score. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 26. | Fossil Fuel Subsidy Burden | Fiscal evaluation quantifying the government budget burden of explicit gasoline and diesel consumer subsidies relative to national GDP. | Direct financial input into evaluating public spending relief potential under the Financial Impact sub-category. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 27. | Utility Revenue Potential | Econometric modeling estimating the additional annual gross revenue national power utilities would capture by electrifying 30% of transport. | Primary financial metric under Market Potential representing the state utility revenue upside in the Impact score. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 28. | Projected Rate of Motorization | Long-term projections of vehicle ownership density per 1,000 people projected out to the year 2050 based on income models. | Key growth metric used to determine future vehicle volume targets under the Market Potential impact category. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 29. | Readiness Total Scores | Aggregated scoring table consolidating the 10 specific readiness-focused sub-indicators (isolating enabling policies, infrastructure, markets, and finance parameters from the broader database) to construct the finalized Readiness Index. | Serves as the official Readiness Index summary table used throughout the report's country profiles and tiering frameworks. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 30. | Impact Total Scores | Aggregated scoring matrix consolidating all 7 impact indicators across climate benefits, public health, growth, and financial relief. | Master Impact Index benchmark used to prioritize international climate finance allocation and development funding placement. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 31. | Readiness and Impact Combined S | Master index table combining Readiness and Impact metrics into equal-weighted averages to establish national priority quadrants. | Primary synthesis deliverable of the database underpinning all flagship report recommendations and country investment classifications; integrates a qualitative Just Transition overlay assessing regional skills gaps, localized training needs, and labor mitigation strategies for ICE job displacement. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |
| 32. | Regional Technical Standards and Customs Classifications Matrix. | Comprehensive mapping of HS codes (for CBUs, CKD kits, cells, and chargers), adopted safety/performance standards (e.g., UN ECE R100 for batteries, national bureaus like KEBS, TBS, RSB), and charging protocols (CCS2, GB/T, CHAdeMO) across all 8 EAC states. | Serves as the regulatory baseline for the tariff harmonization roadmap, establishes cross-border technical interoperability along regional transport corridors, and flags non-tariff trade barriers. | Acquired: Sub-sheet dataset from the Energy for Growth Hub Africa EV Readiness Database. |

Data Significance, and Future Roadmap

1. Current Data Position and Project Significance

The project has successfully secured an extensive, multi-layered data foundation spanning 32 core datasets. By utilizing a dual approach aggregating macro-level indices alongside hyper-localized pilot telematics we have bypassed the traditional data-scarcity traps that often halt regional e-mobility research.

The primary structural anchor of our current framework, the Africa EV Readiness Database (sourced from the Energy for Growth Hub), provides an invaluable, pre-compiled comparative engine across all 54 African nations. When paired with real-world spatial data extracted via Google Maps APIs and actual motorcycle (boda-boda) operational logs, this baseline allows us to move beyond abstract theory. We can now model exact localized unit economics, grid stresses, and market constraints within the East African Community (EAC) with high precision.

2. Justification for the Data Horizon (2021–2026 Timelines)

The datasets intentionally leverage a data duration spanning from 2021 to 2026. This specific multi-year timeline is not a constraint, but a deliberate chronological strategy essential for tracking an emerging market:

- The 2021–2023 Baseline (Policy & Macro Foundations): Captures the foundational era of African e-mobility, during which major national strategies (such as Rwanda’s 2021 strategic e-mobility incentives and early macro-motorization models) were first gazetted.

- The 2024–2025 Mid-term (Operational Growth): Reflects the critical operational shift from small-scale pilots to commercial deployment, yielding high-fidelity telemetry data and real-world grid reliability updates.

- The 2026 Horizon (Current Realities): Integrates the most up-to-date regional standards, current common external tariffs, and recent grid expansion models to reflect today's market landscape.

By combining the structural data of the early 2020s with the dynamic operational telemetry of 2026, the database successfully captures trajectory rather than just a snapshot. This prevents the project from being skewed by temporary market anomalies or short-term post-pandemic economic fluctuations.

3. The Need for Primary Data to Achieve Project Sufficiency

While our current dataset relies on strong institutional proxies, published academic research, and virtual knowledge baselines, transitioning this project from a diagnostic framework into a fully actionable implementation roadmap requires direct, uncompromised primary data.

To achieve complete technical and regulatory sufficiency, the project must move away from proxy estimations for the remaining EAC states. Acquiring specific, un-aggregated internal data such as exact vehicle registration registries, utility sub-station peak load curves, and precise draft policy timelines will eliminate margins of error. This primary data is critical to:

- Ensure recommended tariff reliefs match active HS Code classifications used by customs border officials.

- Pinpoint exact geographic bottlenecks for cross-border transport corridor charging networks.

- Formulate targeted Just Transition upskilling programs backed by exact labor figures from local mechanical associations.

4. Strategic Recommendations for Institutional Data Access (Letters of Request)

To bridge the gap between our current baseline and total data accuracy, we recommend the immediate deployment of formal Letters of Request to key regional custodians. These requests must be highly specific, legally grounded, and targeted as follows:

- To National Revenue & Transport Authorities (e.g., KRA, TRA, Rwanda Transport Development Agency):

  - Request: Granular extracts of vehicle registration databases filtered by propulsion type (ICE vs. EV) and weight class, alongside the current internal classification guidelines for CKD (Completely Knocked Down) and SKD (Semi-Knocked Down) electric vehicle kits.

- To National Power Utilities & Regulators (e.g., Kenya Power, TANESCO, REG, EPRA):

  - Request: Sub-station level peak demand logs, historical grid reliability indices (SAIDI/SAIFI metrics), and active timelines or requirements for setting up specialized EV charging tariffs.

- To National Bureaus of Standards (e.g., KEBS, TBS, RSB):

  - Request: Full text and adoption statuses of regional standards concerning battery safety (e.g., alignment with UN ECE R100), swapping station configurations, and grid plug interoperability protocols.

- To Regional Private E-Mobility Operators & Networks:

  - Request: Aggregated, anonymized charging station uptime logs and fleet energy efficiencies to ground the macroeconomic utility revenue potential models in empirical reality.

By establishing these formal data-sharing pipelines, the EAC Secretariat and project stakeholders will transform this database from a static report into a living, dynamic data system capable of guiding real-world investments and policy harmonization for years to come.

# PRELIMINARY REVIEWS AND FINDINGS

## Situational Diagnosis and Baseline Assessments

In order to gain a perspective of what exists in the EAC region, the consultant will conduct a diagnostic of the current situation of e-mobility in each Partner State, focusing on policy frameworks, evolution and statistics, fiscal incentives if applicable, public perception,  and general environmental assessments including carbon emissions. Some of the initial findings are presented in section 1.1.2 above. Much of the information will be gathered through research on stakeholders’ websites, the internet and published research material. The collected data will first be shared with the concerned entities for validation before inclusion in the reports. Where the virtual data mining will be found to be insufficient, limited physical visits will be arranged, upon consultation and approval of the Client.

In addition to the regional assessments, a review of continental and global practices will be carried out, for the purposes of gauging where the EAC region is compared to the rest of the World. This comparison will serve the purpose of challenging the counties in the EAC to aspire to improve from their current situations, if below continental and global levels.

The baseline assessments will be used for future tracking of progress in each country. The data will be clustered in categories for ease of reference and will include but not limited to numbers of EVs, taxation, policies, pollution levels and any other information that can be measured and tracked.

## Current status of e-mobility in the EAC Region

A preliminary review of the current situation in the EAC shows that electric mobility in the East African Community sits at different stages in each of the Partner States. Three factors shape these different stages: the available amount of electricity, government legislation, and company-backed market building from the ground up.

Kenya and Rwanda lead on adoption and charging infrastructure, while Uganda leads on manufacturing through Kiira Motors Corporation. Tanzania sees an EV import duty reduction from 25% to 10%. Burundi, Somalia and South Sudan remain at an early stage, while the Democratic Republic of the Congo has a very small EV market of its own, though it holds cobalt reserves and the mineral is used in traditional EV batteries.

Preliminary Country-specific status are presented below. These will be updated during the diagnostic phase of the assignment with more accurate data obtained from further consultations with stakeholders and published country statistics.

4.2.1	Burundi

Burundi has low levels of deployment to date, but high ambition in terms of policy. The 2026/2027 Finance Law, passed in 2026, includes Article 221 that mandates that all passenger cars ordered for importation must be EV or hybrid vehicles as of 1 January 2027. The same is to be applied to state procurements, but no information was included in the law on how the scheme will be implemented, nor how used EV imports will be treated. The country’s public transport company has received 25 EV tricycles manufactured by Mahindra. Burundi’s first solar-powered EV charging station was opened in Bujumbura in March 2026, a project financed by CRDB Bank Burundi. Charging infrastructure exists only in Bujumbura, and national electricity access stands at 20.1% of the population, which will shape how realistically the 2027 mandate can be met.

4.2.2	Democratic Republic of Congo

EV adoption in the DRC is still negligible despite zero import duties. Electric cars have faced 0% customs duty and 0% VAT since 2025. This has not been the barrier; instead, it has been electrification rates: 22.5% of the population and closer to 1% in rural areas, a slow customs procedure and intermittent border closures due to political unrest through 2026. Where EVs have been adopted, they are in two isolated clusters. Kinshasa, where the government signed a memorandum of understanding with Vietnam's Vingroup in December 2025, followed by a further agreement in February 2026 with the local firm Exposure SARL to develop an electric taxi service, under a plan that envisions VinFast eventually supplying 500 electric buses and 1,000 electric cars to the city's public and commercial fleet. This remains at the roadmap and feasibility stage rather than vehicles on the road, and Kinshasa currently has only a handful of functioning public charging points. There is Goma, where an independent hydropower supply outside of the national grid has supported the development of a small local market for electric motorcycles.

4.2.3	Kenya

Kenya is by far the best-tracked EV market in the region. Kenya's electric vehicle market reached 24,754 cumulative registered units by February 2026, and further scaled past 35,000 units by mid-2026. The vast majority of that is electric motorcycles, while only 0.18% of newly registered motor vehicles in 2024 were electric. The country has fewer than 1,000 battery electric vehicles on the road, against the 5,500 estimated for Rwanda. This is because import duty on four-wheelers remains one of the factors skewing the market. The National Electric Mobility Policy was unveiled in 2025 and launched in February 2026, backed by tax breaks, positioning the country as East Africa's electric mobility hub. Kenya also has an established infrastructure, with approximately 200-300 public charge points in 2026, second in Africa to Egypt’s inventory, with the Kenya Power e-mobility tariff behind some of that expansion, complemented by increasingly assertive service providers including Roam, BasiGo and Enda.

4.2.4	Rwanda

Rwanda prepared a strategic paper on electric mobility adaptation in 2021 and, in 2025, amended its Transport Policy to include e-mobility.

Rwanda has the most organised policy framework in the region, and it shows in the outcomes. Beginning in January 2025, Kigali banned new petrol motorcycle-taxi registrations. The government requires 30% of state vehicle procurement to be electric, and in 2026, Rwanda became the first African nation that mandated all competing EV companies to use the same interchangeable battery systems. Charging electricity must be priced at a maximum of $0.10 per kWh, half the standard tariff.  As a market, Rwanda has by far the most electric vehicles on the road, at about 5,500, with dense commercial networks from Spiro and Ampersand and more than 20,000 multi-brand battery swaps per day in Rwanda and Kenya combined. Rwanda is the clearest regional reference point for what a fully aligned national framework can achieve.

4.2.5	Somalia

Somalia does not yet have an e-mobility policy or a history of state-organised EV promotion. Private enterprise and civil society have taken the lead thus far. The Somalia Electric Mobility Association (SEMA) was formed to align the industry, investment and standards efforts. It appears that the largest and most near-term technology options for EVs in Somalia are three-wheelers and motorcycles, with an estimated 50,000 motorcycles operating commercially in the city of Mogadishu. The single constraint to widespread EV adoption is the capacity of the national electric grid. The grid is the key limitation: the maximum net grid installed capacity is expected to be 392 MW by 2030, and national electricity access is 7.1%. Almost all e-mobility will take place on solar home systems rather than a public charging network. Somalia's position is closer to a from-scratch market than any other Partner State besides South Sudan.

4.2.6	South Sudan

South Sudan has the lowest electricity access in the Community, at 5.4%, and no dedicated e-mobility policy, but the groundwork is moving through government initiatives. The Ministry of Transport tabled a Revised Transport Sector Policy (2026-2036) before parliament in 2026, explicitly proposing hybrid and electric vehicles as an emerging technology for the sector. The framework is not yet approved, but once operationalized it is intended to provide the basis for an integrated transport system and to catalyze a dedicated E-Mobility Policy. On the ground, a 20 MW solar-plus-storage plant was commissioned in Juba in January 2025, and domestic manufacturer Doshi Motors has produced the country's first locally built EV, the Juba EV, though rolling power cuts introduced in March 2026 underline how far the grid still needs to go.

4.2.7	Tanzania

Tanzania was projected to be East Africa’s fastest-growing e-mobility market by 2023, with an estimated 5,000 EVs by that time. The sector then faced challenges related to high import taxes, a low level of skilled technicians, a lack of public awareness of EV benefits, and uncertain regulations. Notably, the situation has markedly changed on the fiscal side in implementation. EV import duty was repealed in the 2026/2027 budget, which cut EV import duty from 25% to 10%; charging equipment will be exempted from VAT in the same period; and public institutions are to start procuring electric vehicles. This move comes as petrol prices surged after the closure of the Strait of Hormuz in January 2026, triggering an even more pressing need for Tanzania to reduce reliance on petroleum. The Tanzania energy transition strategy also includes the use of Compressed Natural Gas (CNG) to power vehicles and a number of taxis and light goods vehicles in Dar es Salaam use this mode of propulsion

4.2.8	Uganda

Uganda is the farthest from all Partner States on its own journey towards substituting imports with domestic manufacturing. The Kiira Motors facility at Jinja, a state-owned firm, was declared Africa’s largest e-bus production facility, whose manufacturing process saw the percentage of local content rise from under 10% in 2021 to nearly 40% by 2026. A five-year export order worth UGX 1 trillion (USD 250 million) for 820 e-buses was signed at the start of 2026. The Ugandan government is already running local e-buses as the E-Bus Xpress service and plans to run 1,500 e-buses in 14 cities, with an ambition to fully electrify public transport by 2030.  Uganda is the clearest regional case for what the industrial pillar of this strategy could look like if replicated, though a 2024 reversal of import duty exemptions shows the fiscal side has not kept pace with the industrial one.

# STAKEHOLDER ANALYSIS AND MAPPING

## Identification of Stakeholders

To ensure a participatory approach to the assignment, key stakeholders in each country will be mapped and the focal points identified and their contact details stored. This will be for the purposes of consultations virtually and physically where possible and for invitations to validation workshops. The buy-in of both policy makers, investors and users is key in ensuring that the policies developed will not have gaps.

The consultant shall develop a detailed matrix of stakeholders in each country which shall contain the name of the institution, its address and the focal points to be contacted during information gathering. This list shall also be useful when inviting participation to the study validation workshops and for sharing reports generated by the Consultant.

Once compiled, the list will be shared with UNEP and EAC for approval and to request Partner States to add or delete inputs as deemed fit.

The initial proposed list of stakeholders will include: UN Agencies, RECs (COMESA, EAC and SADC) Secretariats and relevant sector departments/institutions, Corridor Management Institutions (CMIs); national ministries responsible for transport, energy, environment, finance, trade and industry; regulators, utilities and standards agencies; EV assemblers, manufacturers, charging companies, financial institutions and fleet operators; city authorities and public transport actors; and development partners, civil society organizations, e-mobility specific association and networks,   academia and research institutions.

So far, the following stakeholders have been identified:

## Global, Continental and Regional Agencies

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | African Union | Issuance of continental guidelines on e-mobility | Eric Ntagengerwa - Head of Transport NtagengerwaE@africa-union.org |
| 2 | United Nations Environment Programme (UNEP) | The Client for the study | Annika Berlin - Programme Management Officer Sustainable Mobility Unit Industry and Economy Division annika.berlin@un.org Jane Akumu - Programme Officer Sustainable Mobility Unit Industry and Economy Division akumu@un.org |
| 3 | United Nations Economic Commission for Africa (UNECA) | Dr. Thomas Lisinge | Dr. Robert Lisinge – Director lisinge@un.org |
| 4 | East African Community Secretariat | Recipient of the study | Robert Achieng – Director Infrastructure rachieng@eachq.org Eng. Godfrey A. Enzama – Principal Civil Engineer genzama@eachq.org |
| 5 | East African Centre for Renewable Energy and Energy Efficiency (EACREEE) | Regional body coordinating the implementation of efficient energy initiatives | Godfrey Muhanguzi Muhumuza g.muhumuza@eacreee.org |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |

## EAC Partner States

    - Republic of Burundi

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Foreign Affairs, Regional Integration and Development Cooperation | Coordination of consultations with stakeholders and validation workshops | Donatien Ndagijimana - Director Infrastructure variella2014@gmail.com |
| 2 | Ministry of Infrastructure, Social Housing, Transport and Environment | Sector ministry responsible for Transport Policy | Marie Jean Kamariza kamazira.mariejeanne@yahoo.fr |
| 3 | Ministry of Mining and Energy Resources, Trade, Industry and Tourism; | Ministry responsible for Energy Generation and Transmission, including establishment of the network of charging stations |  |
| 4 | Ministry of Environment, Agriculture and Livestock | Monitoring the emissions standards in cities and issuing related regulations |  |
| 5 | Ministry of Finance, Budget and Digital Economy | Setting up of taxes on EVs and issuing any legislation related to e-mobility pricing |  |
| 6 | Ministry of Interior | Enforcement of regulations through the National Police |  |
| 7 | OTRACO (public transport operator) | Perspectives on the types of public transport EVs and promotion of the same into the market |  |
| 8 | The Burundi Bureau of Standardization (BBN) | Conformity assessments of batteries and other EV parts |  |
| 9 | REGIDESO (national electricity utility) | Providing charging meters and setting the charging rates for EVs |  |

    - Democratic Republic of Congo

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Transport | Lead ministry | LINDO Dina Jean Roger jrlindodina@gmail.com |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

    - Republic of Kenya

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Roads and Transport State Department for Transport | Sector State Department responsible for Transport Policy | Mr. Paul Kinyua King’ori - Director, Road Transport, State Department for Transport kingoripkk@gmail.com Ms. Racheal Wanyamawi – Acting. Assistant Director Road Transport/ Team Lead for eMobility, State Department for Transport wanyamawinjira@gmail.com / racheal.wanyamawi@transport.go.ke |
| 2. | Ministry of Roads and Transport State Department for Roads | Sector State department for Roads infrastructure | Eng. Kevin Mwandoe – State Department for Roads kmwandoe@gmail.com / kmwandoe@roads.go.ke |
| 3 | Ministry of Energy and Petroleum | Sector State Department Responsible for Energy Policy | Eng. Carl Otwack, Renewable Energy Directorate, State Department for Energy cotwack@gmail.com |
| 4 | Ministry of Trade and Industrialization | Sector State Department responsible for Industry Policy | Mr. Gideon Oele, Director, Engineering and Construction Directorate, State Department for Industry gideon_oele@yahoo.com Eng. Elijah Akumu, Deputy Director, Engineering and Construction Directorate, State Department for Industry eliakumu@gmail.com |
| 5 | The National Treasury | Sector ministry responsible for finance | Mr. Samuel Tsuma, Deputy Director, Fiscal and Macro Directorate, The National Treasury samueltsuma@gmail.com |
| 6 | Ministry of Environment, Climate Change and Forestry | Sector Ministry responsible for Environment and Climate Change | Mr. Brian Mounde, Senior Climate Change Officer, Climate Change Directorate, State Department for Environment and Climate Change brianmounde@gmail.com |
| 7 | Kenya Power and Lighting Company (KPLC) | Utility responsible for power distribution | Eng. David Mugambi, Departmental Manager, Transport services, KPLC dmugambi@kplc.co.ke |
| 8 | Kenya Bureau of Standards (KeBS) | Sector institution responsible for Standards | Eng. Alex Mboa, Principal Standards Officer, KEBS amboa@kebs.org |
| 9 | Energy and Petroleum Regulatory Authority (EPRA) | Regulator in Energy | Eng. Silas Sanga, Assistant Director, Environment, Health and Safety, EPRA silas.sanga@epra.go.ke |
| 10 | Nairobi Metropolitan Area Authority (NaMATA) | Urban transport planning and zoning / fleet electrification | Eng. James Mwaniki , Acting Deputy Director Operations, NaMATA mwaniki.james.g@gmail.com |
| 11 | Electric Mobility Association of Kenya (EMAK) | Umbrella Association of OEMs, and companies involved in Electric mobility | Mr. Hezbon Mose, President EMAK, mose.hezbon@ampersand.solar / kenyaemobility@gmail.com / eo@e-mobilitykenya.org |
| 12 | Federation of Public Transport Sector (FPTS) | Umbrella association for Public Transport Vehicles / fleet electrification | Mr. Edwins Mukabana – President, FPTS Emukabanah@gmail.com |
| 13. | Strathmore University | Academic institution part of the Kenya National e-Mobility Technical Working Group | Eng. Ignatius Maranga, Lecturer , Strathmore University imaranga@strathmore.edu |
| 14. | Transport Futures | Think Tank/ research institution on Sustainable transport | Eng. Mercy Edna Manyasa, Director , Transport Future |

    - Republic of Rwanda

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Infrastructure | Sector ministry responsible for transport policies and infrastructure development | Theogene Dusabumuremyi - Ag. Director General in charge of Transport Transport Directorate theo.dusabumuremyi@mininfra.gov.rw |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

    - Federal Republic of Somalia

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Transport and Communications | Development of Transport Policy | Najma Mohamud Mohamed SPU@motca.gov.so najma.m.mohamoud@gmail.com |
| 2 | Ministry of Foreign Affairs and EAC Affairs | Coordination of regional matters | Mahad Shooli pid.eac@mfa.gov.so |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

    - Republic of South Sudan

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Transport | Lead ministry for mobility policy and regulation | Eng. Lado Tombe Pitiya - Director General for Road Transport ladotangun@gmail.com |
| 2 | Ministry of Energy & Dams | Integration of EV charging with national grid and renewable energy |  |
| 3 | Ministry of Finance & Planning | Setting fiscal incentives, subsidies, and investment frameworks |  |
| 4 | Ministry of Environment & Forestry | Ensuring climate resilience and environmental safeguard standards and regulations are met and adhered to |  |
| 5 | Ministry of Roads & Bridges | Responsible for infrastructure planning and construction of EV‑ready roads and related ancillary structures. |  |
| 6 | South Sudan Urban Development Authority | Urban transport planning and zoning |  |
| 7 | Local bus and minibus operators | Fleet electrification |  |
| 8 | EV importers and distributors | Supply chain and market development |  |
| 9 | Construction & engineering firms | Construction of charging stations and smart grid integration |  |
| 10 | Telecom companies | Setting up digital payment systems for e‑mobility services |  |
| 11 | Universities & technical institutes | Research, training, and innovation |  |
| 12 | Transport unions & associations | Assisting in workforce transition and enforcement of safety standards among members |  |
| 13 | Community groups & NGOs | Advocacy, public education and inclusion of women, youth, and vulnerable populations |  |

    - The United Republic of Tanzania

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 | Ministry of Transport | Sector ministry in charge of e-mobility policy | Augustino Andrew Kambi kambi.augustino@uchukuzi.go.tz |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

    - Republic of Uganda

| No | Name and address of the institution | Role in the Assignment | Contact person and e-mail address |
| --- | --- | --- | --- |
| 1 |  |  | Kharim Kibuuka karim50kib@yahoo.com Immaculate immynyamzy@yahoo.com |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

# DRAFT EAC REGIONAL E-MOBILITY STRATEGY AND POLICY

Upon completion and acceptance of the Diagnostic Study Report the consultant will prepare the policy framework. This framework will be developed in thematic areas through analysis of the situation in each country in a horizontal matrix and then proposing the most appropriate parameters to adopt for the region. The selection could be the most robust of all or in the absence of a suitable local parameter, adoption of the continental or global recommendations will be advised. The thematic areas will be found in the diagnostic report and from suggestions from stakeholders.

The contents of the diagnostic report must be credible and, therefore, should be based on firm evidence. In this regard, any data collected will be corroborated by the national focal points before inclusion in the draft and final reports.

The development of the draft policy will be carried out simultaneously with the preparation of a policy matrix which will contain specific recommendations for each country to adopt, with an implementation road map. This matrix will be reviewed periodically during EAC policy organ meetings in order to give strategic directions to counties on actions needed to keep on track. The matrix will take into account the asymmetrical geometry of Partner States in terms of financial readiness

# CONSULTANT’S MOBILIZATION STATUS

The Contract between Hosea Yimbo Nyangweso and UNEP was signed on 15th September, 2026 for the consultancy services to develop a regional e-mobility Policy and Strategy for the East African Community.  The contract effectiveness date is 15th September 2026 with immediate commencement (i.e contract commencement date is 15th September 2026 with the end date set for 15th March 2027.

The consultant will be assisted in the assignment by a Research Assistant, Michelle Akoth and a Data Analyst, Kenneth Abuto. The team embarked on the initial planning exercise for the assignment on 15th September 2026, commencing with the preparation of this Inception Report and the collection of data on e-mobility available online.

Upon submission of the Inception Report, the consultant will hold an entry meeting with the Client to agree on the study work plan and the data collection methodology. The EAC has already provided a letter of introduction addressed to the eight Partner States requesting for support in conduct of the study. This letter will greatly assist in obtaining data and pertinent information on e-mobility in the EAC.

# WORK PLAN

The following work plan, which fits within the 6-month contract period, will be followed in the implementation of the assignment:

Table 8-1: Work Plan

| Task/Deliverable | Project Week | Start Date | Duration (Days) | End Date | Owner |
| --- | --- | --- | --- | --- | --- |
| Contract signature / kick-off | Week 0 | 2026-09-15 | 0 | 2026-09-15 | UNEP / Consultant |
| - Inception Report | Week 2 | 2026-09-15 | 14 | 2026-09-29 | Consultant |
| - Draft Diagnostic and Assessment Report | Week 6 | 2026-09-29 | 31 | 2026-10-30 | Consultant |
| Review of the diagnostic findings and commentary by the Client | Week 9 | 2026-11-02 | 14 | 2026-11-16 | UNEP / EAC |
| - Final Diagnostic and Assessment Report | Week 11 | 2026-11-16 | 14 | 2026-11-30 | Consultant |
| - Draft EAC Regional E-Mobility Strategy and Policy | Week 17 | 2026-11-30 | 42 | 2027-01-11 | Consultant |
| - Draft Implementation Roadmap and Action Plan, and - Draft Monitoring, Evaluation and Learning Framework. | Week 21 | 2027-01-11 | 28 | 2027-02-08 | Consultant |
| Regional validation workshop | Week 24 | 2027-02-08 | 23 | 2027-03-03 | EAC/UNEP/Partner States |
| - Final EAC Regional E-Mobility Strategy and Policy, and - Final Implementation Roadmap and Action Plan, and - Final Monitoring, Evaluation and Learning Framework. | Week 26 | 2027-03-03 | 28 | 2027-03-31 | Consultant / UNEP/EAC |

# NEXT STEPS

Following the acceptance of the Inception Report, the consultant shall embark on the data collection and the preparation of the Diagnostic Assessment Report.

In the course of data collection, it may be necessary to interview some key stakeholders, especially from the ministries responsible for transport policy and some investors and users. Limited missions to selected countries would be needed. The countries selected for field visits are Kenya, Uganda, Rwanda and Tanzania, based on their advanced levels of promoting electric mobility. The outcomes will be used to develop regional parameters and policy recommendations to be adopted by all the Partner States. In addition, the recommendations of the continental framework on e-mobility will be taken into account.

The consultant will discuss with the Client the possibilities and the modalities of site visits. The following table is indicative of how the visits, if approved, shall be conducted.

Table 9-1: Rwanda Field Mission Plan

| Stakeholder / Facility | Location | Logistics Plan |
| --- | --- | --- |
| Ministry of Infrastructure | Kigali | Field mission conducted by the Research Assistant. Fly to Kigali from Nairobi and visit the institutions over two days Three (03 ) per diem nights |
| tbd | Kigali |  |

Table 9-2: Uganda Field Mission Plan

| Stakeholder / Facility | Location | Logistics Plan |
| --- | --- | --- |
| Ministry of Works and Transport | Kampala | Field mission conducted by the Data Analyst. Fly to Entebbe from Nairobi and visit the institutions over two days Three (03 ) per diem nights |
| tbd | Kampala |  |

Table 9-3: Tanzania Field Mission Plan

| Stakeholder / Facility | Location | Logistics Plan |
| --- | --- | --- |
| Ministry of Transport | Dar es Salaam | Field mission conducted by the Lead Consultant. Fly to Dar es Salaam from Nairobi and visit the institutions over two days Three (03 ) per diem nights |
| tbd | Dar es Salaam |  |

Table 9-4: Kenya Field Mission Plan

| Stakeholder / Facility | Location | Logistics Plan |
| --- | --- | --- |
| Ministry of Roads and Infrastructure | Nairobi | Field mission conducted by the Research Assistant. Fly to Dar es Salaam from Nairobi and visit the institutions over two days No per diem nights. |
| tbd | Nairobi |  |