## E-Mobility Gantt Project
EAC Regional E-Mobility Policy and Strategy
Project Timeline & Gantt Schedule (6 Months ¦ September 2026 - February 2027)
Deliverable Task | Project Week Target | Start Date | Duration (Weeks) | Duration (Days) | End Date | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Contract signature / kick-off | Week 0 | 2026-09-07 | 0 | 0 | 2026-09-07
Inception report | Week 2 | 2026-09-07 | 2 | 14 | 2026-09-21
Draft diagnostic report | Week 8 | 2026-09-21 | 6 | 42 | 2026-11-02
Validation of diagnostic findings | Week 10 | 2026-11-02 | 2 | 14 | 2026-11-16
Final diagnostic report | Week 12 | 2026-11-16 | 2 | 14 | 2026-11-30
Draft strategy and policy | Week 16 | 2026-11-30 | 4 | 28 | 2026-12-28
Draft action plan and M&E framework | Week 18 | 2026-12-28 | 2 | 14 | 2027-01-11
Regional validation workshop | Week 20 | 2027-01-11 | 2 | 14 | 2027-01-25
Final documents | Week 24 | 2027-01-25 | 4 | 28 | 2027-02-22