## Weekly Tracking Data
EAC E-Mobility Regional Strategy - 24-Week Cumulative Progress Schedule
Project Week | Calendar Date | Deliverable/Milestone | Lead Owner | Planned Target Progress | Actual Dynamic Progress
Week 0 | 07-Sep-2026 | Contract signature / kick-off | UNEP / EAC | 0% | 100%
Week 1 | 14-Sep-2026 | Inception Phase Initiated | Consultant | 2% | 50%
Week 2 | 21-Sep-2026 | Inception report submitted | Consultant | 5% | 0%
Week 3 | 28-Sep-2026 | Diagnostic Baseline Setup | Consultant | 10% | 0%
Week 4 | 05-Oct-2026 | National Data Collection | Partner States | 15% | 0%
Week 5 | 12-Oct-2026 | Grid Readiness Assessment | Consultant | 20% | 0%
Week 6 | 19-Oct-2026 | Value Chain & Mineral Mapping | Consultant | 25% | 0%
Week 7 | 26-Oct-2026 | Draft Diagnostic Synthesis | Consultant | 30% | 0%
Week 8 | 02-Nov-2026 | Draft diagnostic report submission | Consultant | 35% | 0%
Week 9 | 09-Nov-2026 | TWG Diagnostic Briefing | TWG | 40% | 0%
Week 10 | 16-Nov-2026 | Validation of diagnostic findings | TWG / Partner States | 45% | 0%
Week 11 | 23-Nov-2026 | Diagnostic Revisions Phase | Consultant | 48% | 0%
Week 12 | 30-Nov-2026 | Final diagnostic report finalized | Consultant | 50% | 0%
Week 13 | 07-Dec-2026 | Policy Matrix Structuring | Consultant | 55% | 0%
Week 14 | 14-Dec-2026 | Fiscal & Tariff Design | Consultant | 60% | 0%
Week 15 | 21-Dec-2026 | Battery Lifecycle Framework | Consultant | 65% | 0%
Week 16 | 28-Dec-2026 | Draft strategy and policy delivery | Consultant | 70% | 0%
Week 17 | 04-Jan-2027 | Implementation Roadmap Setup | Consultant | 75% | 0%
Week 18 | 11-Jan-2027 | Draft action plan & M&E framework | Consultant | 80% | 0%
Week 19 | 18-Jan-2027 | Stakeholder Mobilisation Setup | UNEP / EAC | 85% | 0%
Week 20 | 25-Jan-2027 | Regional validation workshop | TWG | 90% | 0%
Week 21 | 01-Feb-2027 | Feedback Consolidation | Consultant | 93% | 0%
Week 22 | 08-Feb-2027 | Policy Alignment Overhaul | Consultant | 95% | 0%
Week 23 | 15-Feb-2027 | Final Package Assembly | Consultant | 98% | 0%
Week 24 | 22-Feb-2027 | Final documents submitted for Ministerial Approval | EAC Council | 100% | 0%

## Weekly Progress Chart
EAC Regional E-Mobility Project Timeline Tracking Dashboard
This chart renders your project progress profile across each individual week. Update columns E and F on the data sheet to see changes live here.